## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Discussion(Form Filling AI) | MUST HAVE | No Dependency | PRIYANSHU RAJ | 3- Completed
S1 | S1 | US-001 | RoadMap Project | MUST HAVE | Lucid Chart | PRIYANSHU RAJ | 3- Completed
S2 | S2 | US-001 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | MUST HAVE | No Dependency | PRIYANSHU RAJ | 3- Completed
S2 | S2 | US-001 | Use Cases Model Research | SHOULD HAVE | Online Websites | PRIYANSHU RAJ | 3- Completed
S3 | S3 | US-001 | Python Discussion and Certification | MUST HAVE | HackerRank | PRIYANSHU RAJ | 3- Completed
S4 | S4 | US-001 | Sql Discussion and Certification | MUST HAVE | HackerRank | PRIYANSHU RAJ | 3- Completed
S5 | S5 | US-001 | Project Discussion Module 1(Voice Input and Language Processing) | MUST HAVE | Web Speech API | PRIYANSHU RAJ | 3- Completed
S6 | S6 | US-001 | Project Discussion Module 2(Workflow Automation and Optimization) | MUST HAVE | CURSOR | PRIYANSHU RAJ | 3- Completed
S7 | S7 | US-001 | Project Discussion Module 3(Integration with existing services) | MUST HAVE | PySql(Supabase), Flask for backend | PRIYANSHU RAJ | 3- Completed
S8 | S8 | US-001 | Project Discussion Module 4(Testing and Deployment) | MUST HAVE | Render | PRIYANSHU RAJ | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 50 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Project Discussion(Form Filling AI) | 2024-12-04 | 2024-12-10 | ARYAN JATHAR | Others | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | RoadMap Project | 2024-12-11 | 2024-12-17 | ARYAN JATHAR | Design | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | 2024-12-18 | 2024-12-20 | ARYAN JATHAR | Others | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Use Case & Model Research | 2024-12-20 | 2024-12-24 | ARYAN JATHAR | Design | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Python Discussion and Certification | 2024-12-25 | 2024-12-30 | ARYAN JATHAR | Coding | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Sql Discussion and Certification | 2024-12-31 | 2025-01-03 | ARYAN JATHAR | Coding | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Project Discussion Module 1(Voice Input and Language Processing) | 2025-01-06 | 2025-01-10 | ARYAN , ANUMEHA | Build | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Project Discussion Module 2(Workflow Automation and Optimization) | 2025-01-13 | 2025-01-17 | PRIYANUS NIKHIL | Coding | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Project Discussion Module 3(Integration with existing services) | 2025-01-20 | 2025-01-24 | AWAZ, NITHIN | Integration Test | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Project Discussion Module 4(Testing and Deployment) | 2025-01-27 | 2025-01-31 | RABI, ABHIRAMI | System Test | 2- In Progress | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentors and team
Sprint 2 | Day 6 | Lack of clarity on specific project goals and workflow steps. | Conducted a team brainstorming session and reviewed the project requirements.
Sprint 3 | Day 9 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.
Sprint 4 | Day 12 | Difficulty in identifying all potential use cases due to incomplete information. | Conducted additional research and consulted online resources to fill gaps.
Sprint 5 | Day 15 | Confusion about model research part | Conducted for more detailed discussion about model requirements
Sprint 6 | Day 16 | Difficulty in debugging Python practice code | Collaborated with Vaibhav and Akshaya to resolve issues
Sprint 7 | Day 19 | SQL queries taking longer than expected | Optimized queries with mentor support
Sprint 8 | Day 23 | Frontend Queries , Authentication Issue | Discuss with team for working model
Sprint 9 | Day 26 | Challenges integrating voice processing with workflows | Scheduled team debugging session
Sprint 10 | Day 31 | Error while Testing | Solved all the errors and bug

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-12-04 | 2024-12-10 | ARYAN JATHAR | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals.
2 | Sprint 2 | 2024-12-11 | 2024-12-17 | ARYAN JATHAR | Prioritizing Python practice | Delaying review of tasks | Maintaining focus on coding | Achieved Python kit completion on time
3 | Sprint 3 | 2024-12-18 | 2024-12-20 | ARYAN JATHAR | Preparing SQL practice | Rushing through SQL concepts. | Asking for help when stuck. | Completed SQL with support from the team
4 | Sprint 4 | 2024-12-20 | 2024-12-24 | ARYAN , ANUMEHA | Participating in Module 1 discussions | Delaying voice input exploration | Collaborating on language processing strategies | Completed voice input prototypes and received team feedback for improvements.
5 | Sprint 5 | 2024-12-25 | 2024-12-30 | NIKHIL , PRIYANSHU | Conduct more detailed discussions on model requirements to avoid confusion. | Making assumptions about model research without proper clarification. | Collaborating with mentors and team members for guidance | Action Taken: Held a detailed discussion to clarify model requirements and research goals.
6 | Sprint 6 | 2024-12-31 | 2025-01-03 | NITHIN , AWAZ | Debug Python code collaboratively to resolve issues faster. | Struggling alone with debugging without seeking help. | Practicing Python regularly and seeking team support when stuck. | Collaborated with Vaibhav and Akshaya to resolve Python debugging issues.
7 | Sprint 7 | 2025-01-06 | 2025-01-10 | RABI , ABHIRAMI | Optimize SQL queries early to avoid delays. | Spending excessive time on inefficient SQL queries. | Seeking mentor support for query optimization. | Optimized SQL queries with mentor guidance to improve efficiency.
8 | Sprint 8 | 2025-01-13 | 2025-01-17 | ARYAN , ANUMEHA | Address frontend and authentication issues proactively. | Ignoring frontend challenges until they become blockers. | Discussing and resolving issues as a team. | Discussed frontend and authentication issues with the team to create a working model.
9 | Sprint 9 | 2025-01-20 | 2025-01-24 | ARYAN , NIKHIL | Schedule debugging sessions for integration challenges. | Delaying resolution of integration issues. | Collaborating on workflow and voice processing integration. | Scheduled a team debugging session to resolve integration challenges.
10 | Sprint 10 | 2025-01-27 | 2025-01-31 | ARYAN , PRIYANSHU | Test modules thoroughly to catch errors early. | Ignoring small errors during testing. | Solving bugs and errors systematically | Resolved all errors and bugs during testing to ensure smooth deployment.